Computer Science Club 2025-2026 plan

- Welcome newcomers with an easy starter contest to assess the levels of club members

- Gauge abilities → separate novices vs advanced coders.

- Outline the year plan with milestones, training, and external contests, University Contests.

- Show adaptability → how you’ll adjust prep once you see the team’s levels.

Here’s a draft you can use (Markdown style, but I can also format into Word/PDF if you want).

# Computer Science Club – Competitive Programming Plan 2025–2026

## Introduction

Our club’s main focus is competitive programming team-based problem solving in the style of the International Collegiate Programming Contest (ICPC). Unlike hackathons, these contests are algorithmic, time-limited, and some are team-oriented.

The goals this year:

- Build strong problem-solving and coding fundamentals (for those that don’t have already)

- Form competitive 3-person teams.

- Train consistently through mock contests and problem sets.

- Compete in university-hosted programming contests and aim for top placements.

- Compete in online competitive programming contest rounds aiming for top placement.

## Step 1: Welcome & Placement Contest

Week 1–2 (right after fair):
 We’ll run a friendly “Kickoff Contest” to test everyone’s coding ability.

- Format:

  - 20 problems, 60 minutes, individual. (Not expected to solve all, the large amount of problems will help us to see who knows which skills)

  - Problems range from easy implementation (loops, arrays) → basic algorithmic (sorting, greedy, simple math).

  - Platforms: HackerRank/Codeforces gym/custom grader.

- Purpose:

  - Get a baseline of member skills.

  - Identify strengths (math background, coding fluency, problem-solving speed).

  - Use results to group people into Novice / Intermediate / Advanced tracks.

## Step 2: Training & Team Formation

Once we know skill levels, we’ll adjust prep accordingly:

- Novices → focus on basic coding fluency (loops, functions, arrays, recursion, brute force).

- Intermediate → start algorithms (greedy, prefix sums, binary search, Dynamic Programming basics).

- Advanced → deep dive into contest algorithms (graphs, flows, geometry, segment trees, optimization problems).

Teams of 3 will be formed by late fall, balanced across strengths (implementer / math / algorithms).Year Plan & Contest Roadmap

Fall 2025:

- Kickoff Contest (internal)

- Weekly workshops (problem solving, algorithms, mock contests).

- Enter PClassic (UPenn) + CALICO Fall (UC Berkeley, online).

- Enter Online Codeforces rounds, AtCoder, Leetcode contests

Winter 2025–26:

- Internal ICPC-style mock contests (3 hours, teams of 3).

- Training on advanced topics (flows, DP optimizations, string algorithms).

- Optional: Meta Hacker Cup/Kick Start style problems for advanced groups.

- Train for the University contests in spring

Spring 2026:

- Compete in CMIMC Programming Contest (Carnegie Mellon).

- PClassic Spring + CALICO Spring.

- Internal “Spring Invitational” (invite nearby schools or just our own).

- Cornell HS Contest (Cornell Tech, NYC).

- Columbia HS Contest (NYC).

- UCLA Codesprint HS Division (remote).

## Reason for functionality

This approach ensures:

- Inclusivity: Everyone can start, no matter their coding level.

- Progression: Structured growth from beginner → advanced competitor.

- Competitiveness: Proven contests like Cornell, Columbia, CALICO, CMIMC, PClassic, UCLA Codesprint.

- Adaptability: The prep plan changes based on actual skill levels measured in the kickoff contest.

## Steps for the start of the club

- Run the kickoff contest in the first two weeks after fair.

- Categorize members & begin workshops.

- Register early for Fall 2025 contests.

- Start creating training material for the upcoming online contests, and university rounds.